## WBS Spreadsheet
Milestone | Task ID | Task | Owner | Duration (days) | Notes
Establish a plant delivery and logistics plan | 1.1 | Source packaging materials | Fulfillment Director | 20 | Coordinate with vendors to ensure timely sourcing of materials and efficient hiring of delivery drivers
| 1.2 | Hire delivery drivers | Human Resources Specialist | 10
| 1.3 | Calculate delivery fees | Financial Analyst | 2 | Work closely with the Fulfillment Director to anaylyze costs and determine appropriate delivery fees
Select and install supply chain software and equipment | 2.1 | Supervise vendor setup of inventory software | Inventory Manager | 5 | Collaborate with vendors to ensure the seamless setup of software for effective inventory management
| 2.2 | Supervise vendor installation of fulfillment software | Inventory Manager | 5 | Oversee the installation process, ensuring equipment functionality aligns with operational requirement
| 2.3 | Determines internal safety protocols for equipment | Quality Assurance Tester | 2 | Define safety protocols and best practices to ensure the equipment is used safely and efficently
Develop and launch an employee training program | 3.1 | Develop training sessions | Human Resources Specialist | 2 | Design comprehensive training sessions that cover the use of both software and equipment for all employees
| 3.2 | Train employee on softwares and equipment | Training Manager | 5 | Implement training sessions and provide hands-on guidance to employees for effective learning
| 3.3 | Monitor progress and improve training process | Training Manager | 14 | Regularly assess employee progress, gather feedback, and refine training processes to enhance effectiveness